## To-Do List
Simple task List
TASK | STATUS | PRIORITY | STORY POINTS | DUE DATE | DELIVERABLE | STATUS KEY | PRIORITY KEY
Review Wordle Game Play | Done | Medium | 1 | 2023-05-12 | Review experience with collegues | To Do | High
Develop an algorithm for scoring guesses | To Do | High | 3 |  | Review algorithm with collegues and senior dev | In Progress | Medium
Create a flow for interaction with the UI | In Progress | Medium | 2 |  | Review with collegues | Done | Low
Write user documentation based on plan | To Do | High | 3 |  | Documentation in readme.md | On Hold
Write test cases based on the documentation | To Do | Medium | 1 |  | Reviewed test cases | Cancelled
Develop guess scoring function | To Do | High | 5 |  | score_guess passes test cases
Develop function to ask for and validate guess | In Progress | High | 3 |  | demonstrate entry of guess in UI
Develop word chooser function | Done | High | 1 |  | pass test automation
Build end-to-end MVP | To Do | High | 5 |  | All test cases pass!
Review MVP with Client | To Do | High | 2 |  | Review with client, senior dev
Review with Senior Development | To Do | High | 2 |  | Review with client, senior dev
<<Additional Tasks and features>> | To Do |  | 8
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
<<Additional Tasks and features>>
Note on E2: Story points An estimate of the relative complexity of a task. If we say task a is 1 story point and task b is 2 story points we mean we believe task b is twice the size of a for us. We typically rate using a Fibonacci sequence to reflect the fact that as tasks grow our ability to estimate becomes less precise: 1, 2, 3, 5, 8, 13, 21, 34, 55, 89

## Alternative platforms
Github | Link | Highlights
Recommended |  |  | All software development projects of a significant size use some form of task management
|  | New project management view! | Task manamgent helps us:
| https://github.com/features/issues | Dev focused | Prioritise
|  | Simple | Coordinate
|  | Free | Communicate
Trello
Today's software development tools focus on keeping task management close to the programs themselves, integrating with version control and other tools.
|  | Established | Simple workflows are increasingly preferred
| https://trello.com/home | Easy to use | Hosting (SaaS) is becoming more popular
|  | Lots of dev friendly integrations | Most popular services offer free entry-level plans
Free limited use
Australian owned
JIRA
Very mature
| https://www.atlassian.com/software/jira | Powerful workflows
Industry-standard for much of the last 15 years
Complex
Australian owned and made
meistertask
Growing in popularity
| https://www.meistertask.com/ | Versatile
Scales
Other notables
Wrike
Asana
todoist
Any.do
Monday.com
Many, many more!
SOFTWARE INDUSTRY TOOLS